## Consolidated Sheet
Things needed to be done | Time needed (hr) | Total Time needed (hrs)
Create the main site with seach bar (calendar) | 0.5 | 36.5
Add filters to the search bar | 2
Create tag for different destinations and connect with the filter | 4
Get hotel and flight information from travel API then connect to the website | 1
Collect real experience and reviews via API and connect with the destionations | 4
Set up register system | 2
Drop down bars with preferences: themes, weather, countries, etc. | 5
Include previews of specific travel destinations: tour sites, food, etc. | 5
Give at least three places according to user's preference | 3
Find/provide the user with the best hotel/resort deals along with car rental if needed | 2
Find/provide user with best flight packages to this trip from their current location | 2
Set up comment section for users to update their own experience | 1
Get informent about tourist attractions | 1
Get visa informations and post with the result | 1
Set up the relation between the filter and the tags on destination and return the most suitable destination | 2
Set up a refresh button to give some other possibe answer | 1

## Yirong Zhang
Things need to be done | Time needed (hr) | Total Time needed (hrs)
Create the main site with seach bar (calendar) | 0.5 | 22
Add filters to the search bar | 2
Create tag for different destinations and connect with the filter | 4
Get hotel and flight information from travel API then connect to the website | 1
Collect real experience and reviews via API and connect with the destionations | 4
Set up register system | 2
Connect the account with social medias | 0.5
Create database for personal preference based on account | 2
Set up comment section for users to update their own experience | 1
Get informent about tourist attractions | 1
Get visa informations and post with the result | 1
Set up the relation between the filter and the tags on destination and return the most suitable destination | 2
Set up a refresh button to give some other possibe answer | 1

## Zonglin Wu
Things need to be done | Time needed (hr) | Total Time needed (hrs)
Design home page | 3 | 26
Design new user registration form | 1
Connect third-party authentication | 1
Create databse for personal information | 1
Select travel plan (add filters on destination, budget and style) | 4
Check popular travel tours | 2
Design your personal travel tours | 2
Add fitlers on time, hotel, tourist attraction | 2
Get the information from travel API | 4
Collect the weather information via weahter API | 3
Share your travel experience | 1
Display the result | 2

## Yanru Chen
Things needed to be done | Time needed (hr) | Total Time needed (hrs)
estimate/average distance from input location to destination | 2 | 30
visa options from source to targeted location (implement visa API) | 2
recommend destinations based on visa options | 4
estimate/average plane time needed from source to target destination | 3
create filter that can select trip by both distance and days | 4
decide how many locations want to show for destination page (per page) | 1
how to arrange these locations (by plane time or geological location) | 3
design how to link visa options to recommendation page | 1
create a planner for trips that saves users wanted destination | 6
create filter that can select continent | 1
design the layout of the filter and priority | 1
design filter that location that are good for family/single person | 2

## Terry Zhen
Things needed to be done | Time needed (hr) | Total Time needed (hrs)
Drop down bars with preferences: themes, weather, countries, etc. | 5 | 19
Include previews of specific travel destinations: tour sites, food, etc. | 5
Give at least three places according to user's preference | 3
Find/provide the user with the best hotel/resort deals along with car rental if needed | 2
Find/provide user with best flight packages to this trip from their current location | 2
Inlcude all apis needed for above todo list items | 2